## MAIN
CMF WORK IN PROGRESS — Updated April 23, 2026
WO # | PO # | COMPANY | JOB NAME | CUST SHIP | PART # | DESCRIPTION | QTY | SCREENSHOT | MATERIAL | THICKNESS | MATL | ENG | LASER | LASER (O) | TUBE LSR(O) | SAW | BAND (O) | BEND | CLEAN | CSK | DRILL | TAP | GRIND | WELD | MACH (O) | PLAT (O) | PAINT | PAINT (O) | SPEC | SPEC (O) | W.JOB (O) | HW | ASSM | DELIVERY DATE | CURRENT STEP | STATUS | NOTES
4272 | 038625491 - R0 | FLYNN | TWH STAIRWELL WALL PART 2 | 2026-04-09
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | M0781-105 | 10 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | 300-0179 | 28 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | M0744-001 | 3 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | M0744-002 | 3 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | 300-0234 | 62 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | M0716-106 | 5 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | M0106-001 | 270 | [26 empty] | 2026-04-09 | GRINDING |  | SAW, DRILL, GRIND
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | M0106-101 | 3 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | M0106-102 | 6 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | M0106-103 | 6 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | 300-0107 | 13 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4272 | 038625491 - R0 | FLYNN |  |  | TWH STAIRWELL WALL PART 2 | 300-0108 | 10 | [26 empty] | 2026-04-09 | WHOLE JOB |  | WHOLE JOB (O)
4418 | 038629650 - R0 | FLYNN | R2a-L6 ST- Site Bulk for Starter Track | 2026-04-13
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH55-01-001 | 200 | [26 empty] | 2026-04-13 | MACHINE (O) |  | MACHINE (O), PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH55-01-002 | 320 | [26 empty] | 2026-04-13 | MACHINE (O) |  | MACHINE (O), PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH55-01-003 | 4 | [26 empty] | 2026-04-13 | MACHINE (O) |  | MACHINE (O), PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-01-001 | 7 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-01-002 | 11 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-02-001 | 7 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-02-002 | 11 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-03-001 | 7 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-03-002 | 11 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-04-001 | 320 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-05-001 | 320 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-06-001 | 320 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-07-001 | 4 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-08-001 | 4 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4418 | 038629650 - R0 | FLYNN |  |  | R2a-L6 ST- Site Bulk for Starter Track | GH107-09-001 | 4 | [26 empty] | 2026-04-13 | SHIP |  | LASER CUT, PLATING (O)
4358 | 016627938 - R0 | FLYNN | Small Fab Parts | 2026-04-13
4358 | 016627938 - R0 | FLYNN |  |  | Small Fab Part | 300-0106 | 500 | [26 empty] | 2026-04-13 | GRINDING |  | BANDSAW (O), GRIND
4358 | 016627938 - R0 | FLYNN |  |  | Small Fab Part | 300-0232 | 200 | [26 empty] | 2026-04-13 | MACHINE (O) |  | BANDSAW (O), MACHINE (O)
4466 | 038630781-R0 | FLYNN | CW1 SHOPBULK - 2 | 2026-04-15
4466 | 038630781-R0 | FLYNN |  |  |  | AB7-001-01 | 1 | [26 empty] | 2026-04-15 | WATERJET (O) |  | WATERJET (O), PLATING (O)
4466 | 038630781-R0 | FLYNN |  |  |  | AB4-001-01 | 18 | [26 empty] | 2026-04-15 | BEND |  | LASER CUT, BEND, PLATING (O)
4466 | 038630781-R0 | FLYNN |  |  |  | AB4-003-01 | 42 | [26 empty] | 2026-04-15 | BEND |  | LASER CUT, BEND, PLATING (O)
4406 | 038629243 - R0 | FLYNN | R302 Non-typical Shop Bulk - Part 2 | 2026-04-17
4406 | 038629243 - R0 | FLYNN |  |  | R302 Non-typical Shop Bulk - Part 2 | G0531-001 | 50 |  | PVC | [24 empty] | 2026-04-17 | SHIP |  | WATERJET (O)
4406 | 038629243 - R0 | FLYNN |  |  | R302 Non-typical Shop Bulk - Part 2 | G0531-011 | 42 |  | PVC | [24 empty] | 2026-04-17 | SHIP |  | WATERJET (O)
4406 | 038629243 - R0 | FLYNN |  |  | R302 Non-typical Shop Bulk - Part 2 | G0531-022 | 2 |  | PVC | [24 empty] | 2026-04-17 | SHIP |  | WATERJET (O)
4406 | 038629243 - R0 | FLYNN |  |  | R302 Non-typical Shop Bulk - Part 2 | G0531-021 | 55 |  | PVC | [24 empty] | 2026-04-17 | SAW |  | SAW, DRILL
4488 | 44786 | HABCO |  | 2026-04-20
4488 | 44786 | HABCO |  |  | C068379 | BRACKET DR MTG TOP RETAINER TORSION SS | 600/750 |  | SS | 14GA | 2026-04-22 |  | 2026-04-22 | [5 empty] | 2026-04-23 |  |  | 2026-04-25 | [11 empty] | 2026-04-27 | CLEAN |  | LASER CUT, CLEAN, TAPPING
4488 | 44786 | HABCO |  |  | C068378 | BRACKET DR MTG TOP BASE 2P TORSION SS | 540/750 |  | SS | 14GA | 2026-04-22 |  | 2026-04-22 |  |  |  |  | 2026-04-24 | 2026-04-23 | [12 empty] | 2026-04-25 |  | 2026-04-27 | CLEAN |  | LASER CUT, CLEAN, BEND, HARDWARE
4451 | 038630410-R0 | FLYNN | R06 Additional shop bulk | 2026-04-21
4451 | 038630410-R0 | FLYNN |  |  |  | M009-002 | 1 | [26 empty] | 2026-04-21 | SHIP |  | MACHINE (O), PLATING (O)
4495 | 60988 | FLO |  | 2026-04-23
4495 | 60988 | FLO |  |  | LM-556-R | BRACKET RAIL APPLICATOR RIGHT | 2 |  | HRPO | 3/8" | [7 empty] | 2026-04-23 | 2026-04-23 | [14 empty] | 2026-04-23 | BEND |  | LASER CUT, CLEAN, BEND
4495 | 60988 | FLO |  |  | LM-556-L | BRACKET RAIL APPLICATOR LEFT | 2 |  | HRPO | 3/8" | [7 empty] | 2026-04-23 | 2026-04-23 | [14 empty] | 2026-04-23 | BEND |  | LASER CUT, CLEAN, BEND
4450 | 44687 | HABCO |  | 2026-04-23
4450 | 44687 | HABCO |  |  | C063859 | PLATE PIVOT DOOR BOT ZINC BLK | 1000 |  | CRS | 11GA | [15 empty] | 2026-04-27 | [7 empty] | 2026-04-30 | PLATING (O) |  | LASER CUT, CLEAN, CSK, WELD, PAINT, PLATING (O)
4450 | 44687 | HABCO |  |  | C065980 | BRACKET DOOR MTG TOP RETAINER SST | 40 |  | SS | 11GA | [9 empty] | 2026-04-23 |  |  |  | 2026-04-25 | [5 empty] | 2026-04-27 |  |  |  | 2026-04-30 | CLEAN |  | LASER CUT, CLEAN, CSK, WELD, SPECIAL (O)
4415 | 420749 | DRIVE PRODUCTS INC |  | 2026-04-23
4415 | 420749 | DRIVE PRODUCTS INC |  |  | WT-CONW45-1-SHO | Console Body w/45 Base Angle - new style | 25 |  | CRS | 14GA | [17 empty] | 2026-04-027 | [5 empty] | 2026-04-23 | PAINT (O) |  | LASER CUT, CLEAN, BEND, HARDWARE, PAINT (O)
4467 | 103843 | TAYCO |  | 2026-04-24
4467 | 103843 | TAYCO |  |  | 8390-0051_R01 8390-0051 | LASER CUT~SLIDING DOOR LOCK BK | 50 |  | HRPO | 3/8" | [7 empty] | 2026-04-23 |  |  |  | 2026-04-23 | [11 empty] | 2026-04-23 | TAPPING |  | MACHINE (O), TAPPING, BEND
4414 | 103608 | TAYCO |  | 2026-04-24
4414 | 103608 | TAYCO |  |  | 8480-0038_R02 8480-0038 | 5/8X3X4 CRS PLATES F/SLIDING D | 100 | [26 empty] | 2026-04-20 | MACHINE (O) |  | MACHINE (O)
4340 | PO164 | KLIMATROL |  | 2026-04-24
4340 | PO164 | KLIMATROL |  |  | KLIMACABI-30247 | Klimatrol White Surface Mount Cabinet 30x24x7 | 5 | [25 empty] | 2026-04-24 | 2026-04-24 | ASSEMBLY |  | ASSEMBLY
4340 | PO164 | KLIMATROL |  |  | KLIMACABI-36247 | Klimatrol White Surface Mount Cabinet 36x24x7 | 2026-04-05 | [25 empty] | 2026-04-24 | 2026-04-24 | ASSEMBLY |  | ASSEMBLY
4340 | PO164 | KLIMATROL |  |  | KLIMACABI-42247 | Klimatrol White Surface Mount Cabinet 42x24x7 | 2026-01-05 | [25 empty] | 2026-04-24 | 2026-04-24 | ASSEMBLY |  | ASSEMBLY
4340 | PO164 | KLIMATROL |  |  | KLIMACABI-48247 | Klimatrol White Surface Mount Cabinet 48x24x7 | 3 | [25 empty] | 2026-04-24 | 2026-04-24 | ASSEMBLY |  | ASSEMBLY
4482 | 103951 | TAYCO |  | 2026-04-27
4482 | 103951 | TAYCO |  |  | 8393-2601161 R00 8393-2601161 | SURF MTD SC,10''Hx30''W,MT,SR | 1 |  | CRS | 16GA |  | 2026-04-24 | 2026-04-24 |  |  |  |  | 2026-04-25 | [15 empty] | 2026-04-27 | LASER CUT |  | LASER CUT, BEND
4481 | CAP2604077 | KNC/KN |  | 2026-04-27
4481 | CAP2604077 | KNC/KN |  |  |  | 20 GA GAL. FOOT GRILLE PAN 20GAGALVANIZEDPAN 20 GA GALVANIZED STEEL PAN1 I.D.: 70" X 34" | 17.25 |  | G-90 | 20GA | [16 empty] | 2026-04-25 | [6 empty] | 2026-04-27 | BEND |  | LASER CUT, CLEAN, BEND
4478 | 208370 | BVGLAZING SYSTEM |  | 2026-04-27
4478 | 208370 | BVGLAZING SYSTEM |  |  |  | MISE HARDWARE 1/2" ALLUMINUM SHIMS-H-2W-05H-3L | 30 | [13 empty] | 2026-04-25 | [12 empty] | 2026-04-27 | DRILL |  | MATERIALS, SAW, DRILL
4461 | CAP2604032 | KNC/KN CROWDER |  | 2026-04-27
4461 | CAP2604032 | KNC/KN CROWDER |  |  |  | 20 GA GAL. FOOT GRILLE PAN 20 GAGALVANIZEDPAN 20 GA GALVANIZED STEEL PAN 44-3/4" X 32-3/4" | 2 |  | G-90 | 20GA | [16 empty] | 2026-04-25 | [6 empty] | 2026-04-27 | SHIP |  | ENGINEERING, LASER CUT, CLEAN, BEND, PAINT
4459 | 103819 | TAYCO |  | 2026-04-27
4459 | 103819 | TAYCO |  |  | 8393-0049_R02 8393-0049 | SWITCH BRACKET FILLER T CONNECTOR | 250/500 |  | CRS | 14GA | [9 empty] | 2026-04-25 | [13 empty] | 2026-04-27 | CSK |  | LASER CUT (O), CSK
4446 | 207938 | BVGLAZING SYSTEM |  | 2026-04-27
4446 | 207938 | BVGLAZING SYSTEM |  |  | 5610-88881340 | 1/2" ALUM SOLID SHIM (H-2W 05H-3L) 5610-88881340 | 1500 | [13 empty] | 2026-04-25 | [12 empty] | 2026-04-27 | DRILL |  | MATERIALS, SAW, DRILL
4446 | 207938 | BVGLAZING SYSTEM |  |  | 5605-88881340 | MISC HARDWARE 1/2" ALUM SOLID SHIM (H-2W 05H-3L) | 1000 | [13 empty] | 2026-04-25 | [12 empty] | 2026-04-27 | DRILL |  | MATERIALS, SAW, DRILL
4434 | 44664 | HABCO |  | 2026-04-27
4434 | 44664 | HABCO |  |  | C067693 | PLATE PIVOT DOOR WIRE BOT | 500 |  | CRS | 11GA | [15 empty] | 2026-04-27 | [7 empty] | 2026-04-30 | PLATING (O) |  | LASER CUT, CLEAN, CSK, WELD, PLATING (O)
4432 | 103719 | TAYCO |  | 2026-04-27
4432 | 103719 | TAYCO |  |  | 8393-0046 - REV 02 8393-0046 | TOP CONNECTOR 90 DEG | 200 |  | CRS | 12GA | [7 empty] | 2026-04-25 | [15 empty] | 2026-04-27 | BEND |  | LASER CUT, CLEAN, TAPPING, CSK, BEND
4426 | CAP2603159 | KNC/KN CROWDER |  | 2026-04-27
4426 | CAP2603159 | KNC/KN CROWDER |  |  |  | 16 GA ALUM. FOOT GRILLE PAN 16 GA ALUMINUM PAN 70" X 34" | 8 |  | ALUMINIUM | 16GA | [16 empty] | 2026-04-25 | [6 empty] | 2026-04-27 | PAINT |  | ENGINEERING, LASER CUT, CLEAN, BEND, PAINT
4426 | CAP2603159 | KNC/KN CROWDER |  |  |  | 16 GA ALUM. FOOT GRILLE PAN 16 GA ALUMINUM PAN 34" X 34" | 15 |  | ALUMINIUM | 16GA | [16 empty] | 2026-04-25 | [6 empty] | 2026-04-27 | PAINT |  | ENGINEERING, LASER CUT, CLEAN, BEND, PAINT
4422 | 301261 | DAVIS STANDARD |  | 2026-04-27
4422 | 301261 | DAVIS STANDARD |  |  | CABC242010PB / - CABC242010PB + 002220362-3-CAB1 | ENCLOSURE,N-12 WALL 24H X 20W X 10DINCLUDES SUBPANEL, PLUs PLATE BOTH SIDES | 1 | [26 empty] | 2026-04-23 | WELD |  | GRIND , ENGINEERING, LASER CUT, TAPPING, BEND, WELD
4422 | 301261 | DAVIS STANDARD |  |  | CABC242012PB / - CABC242012PB + 002225481-2-CAB1 | ENCLOSURE,N-12 WALL 24H X 20W X 12D INCLUDES SUBPANEL, PLUG PLATE BOTH SIDES | 2 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4422 | 301261 | DAVIS STANDARD |  |  | CABC362412PB / - CABC362412PB + 002222827-47-CAB2 | ENCLOSURE,N-12 WALL 36H X 24W X 12D INCLUDES SUBPANEL, PLUG PLATE BOTH SIDES | 1 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4422 | 301261 | DAVIS STANDARD |  |  | CABC242010PB / - CABC242010PB + 002220362-7-CAB1 | ENCLOSURE,N-12 WALL 24H X 20W X 10DINCLUDES SUBPANEL, PLUG PLATE BOTH SIDES | 1 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4422 | 301261 | DAVIS STANDARD |  |  | CABC242010PB / - CABC242010PB + 002220362-11-CAB1 | ENCLOSURE,N-12 WALL 24H X 20W X 10DINCLUDES SUBPANEL, PLUG PLATE BOTH SIDES | 1 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4422 | 301261 | DAVIS STANDARD |  |  | CABC242012PB / - CABC242012PB + 002225481-5-CAB1 | ENCLOSURE,N-12 WALL 24H X 20W X 12D INCLUDES SUBPANEL, PLUG PLATE BOTH SIDES | 1 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4422 | 301261 | DAVIS STANDARD |  |  | CABC362412PB / - CABC362412PB + 002226456-8-CAB1 | ENCLOSURE,N-12 WALL 36H X 24W X 12D INCLUDES SUBPANEL, PLUG PLATE BOTH SIDES | 1 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4412 | 13265 | W A ELECTRIC |  | 2026-04-27
4412 | 13265 | W A ELECTRIC |  |  |  | 121B1065P2 PANEL | 20 |  | CRS | 11GA | [17 empty] | 2026-04-27 | [5 empty] | 2026-04-30 | PAINT (O) |  | LASER CUT, PAINT (O)
4412 | 13265 | W A ELECTRIC |  |  |  | 121B1065P2 PANEL | 25 |  | CRS | 11GA | [17 empty] | 2026-04-27 | [5 empty] | 2026-04-30 | PAINT (O) |  | LASER CUT, PAINT (O)
4401 | 301009 | DAVIS STANDARD |  | 2026-04-27
4401 | 301009 | DAVIS STANDARD |  |  | CABC363214F CABC363214F + 0022171432-32-CAB1 | CABINET, FLAT FRONT $1,425.00 FRONT ACCESS, 36H X 32W X 14D, W/FLANGE DISC. INCLUDES DOOR AND SUBPANEL, NO PAINT | 1 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4401 | 301009 | DAVIS STANDARD |  |  | CABC363214F CABC363214F + 0022171432-34-CAB1 | CABINET, FLAT FRONT FRONT ACCESS, 36H X 32W X 14D, W/FLANGE DISC. INCLUDES DOOR AND SUBPANEL, NO PAINT | 1 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4401 | 301009 | DAVIS STANDARD |  |  | CABC242412F CABC242412F + 002217142-39-CAB1 | CABINET, FLAT FRONT FRONT ACCESS, 24H X 24W X 12D, W/FLANGE DISC. INCLUDES DOOR, NO PAINT | 1 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4401 | 301009 | DAVIS STANDARD |  |  | CABC242410O CABC242410O + 002217142-18-CAB1 | CABINET, OCS 24H X 24W X 10D, 1-DOOR, W/SUBPANEL, W/CUTOUTS CUTOUTS FOR HANDLES AND 80MM SWINGARM TOP/BOT | 1 | [26 empty] | 2026-04-23 | WELD |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4401 | 301009 | DAVIS STANDARD |  |  | DS97593 / - DS97593 + 002217142-27-CAB1 | ENCLOSURE FRONT ACCESS, 52.7H X 40W X 14D, W/FLANGE DISC.INCLUDES DOORS, SUBPANEL, NO PAINT (SUNAN USE ONLY | 1 |  |  |  |  | 2026-04-24 | 2026-04-24 |  |  |  |  | 2026-04-27 |  |  |  | 2026-04-27 | 2026-04-29 | 2026-04-28 | [9 empty] | 2026-04-30 | LASER CUT |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4401 | 301009 | DAVIS STANDARD |  |  | CABC477014F / A CABC477014F + 002217142-36-CAB1 | CABINET, FLAT FRONT FRONT ACCESS, 47H X 70W X 14D, W/FLANGE DISC FLANGE DISCONNECT ON THE LEFT END OF CABINET, SOLID SIDE WALLS USE DS PART# DS26349 FOR BLANK PLUG PLATES | 1 |  |  |  |  | 2026-04-24 | 2026-04-24 |  |  |  |  | 2026-04-27 |  |  |  | 2026-04-27 | 2026-04-29 | 2026-04-28 | [9 empty] | 2026-04-30 | LASER CUT |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4393 | PO-044528 | HABCO |  | 2026-04-27
4393 | PO-044528 | HABCO |  |  | C065980 | PLATE PIVOT DOOR BOT SST | 40 |  | SS | 11GA | [19 empty] | 2026-04-27 |  |  | S | 2026-04-30 | SPECIAL (O) |  | LASER CUT, CLEAN, CSK, WELD
4505 | 3005809 | ACTION HOME SERVICE |  | 2026-04-28
4505 | 3005809 | ACTION HOME SERVICE |  |  |  | 20"W X 23" HO PANEL | 1 |  | G-90 | 14GA | 2026-04-22 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-27 | [15 empty] | 2026-04-28 | LASER CUT |  | ENGINEERING, LASER CUT, BEND
4504 | 3005594 | ACTION HOME SERVICE |  | 2026-04-28
4504 | 3005594 | ACTION HOME SERVICE |  |  |  | 36" X 42" POOL PANEL | 1 |  | G-90 | 14GA | 2026-04-22 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-27 | [15 empty] | 2026-04-28 | LASER CUT |  | ENGINEERING, LASER CUT, BEND
4504 | 3005594 | ACTION HOME SERVICE |  |  |  | 48" X 42" POOL PANEL | 1 |  | G-90 | 14GA | 2026-04-22 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-27 | [15 empty] | 2026-04-28 | LASER CUT |  | ENGINEERING, LASER CUT, BEND
4504 | 3005594 | ACTION HOME SERVICE |  |  |  | 84" X 42" POOL PANEL | 1 |  | G-90 | 14GA | 2026-04-22 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-27 | [15 empty] | 2026-04-28 | LASER CUT |  | ENGINEERING, LASER CUT, BEND
4503 | 3005112 | ACTION HOME SERVICE |  | 2026-04-28
4503 | 3005112 | ACTION HOME SERVICE |  |  |  | 24" X 42" POOL PANEL | 1 |  | G-90 | 14GA | 2026-04-22 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-27 | [15 empty] | 2026-04-28 | LASER CUT |  | ENGINEERING, LASER CUT, BEND
4503 | 3005112 | ACTION HOME SERVICE |  |  |  | 48" X 42" POOL PANEL | 1 |  | G-90 | 14GA | 2026-04-22 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-27 | [15 empty] | 2026-04-28 | LASER CUT |  | ENGINEERING, LASER CUT, BEND
4503 | 3005112 | ACTION HOME SERVICE |  |  |  | 84" X 42" POOL PANEL | 1 |  | G-90 | 14GA | 2026-04-22 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-27 | [15 empty] | 2026-04-28 | LASER CUT |  | ENGINEERING, LASER CUT, BEND
4465 | 60952 | FLO |  | 2026-04-29
4465 | 60952 | FLO |  |  | LM-220-4-.125 | MANIFOLD ELPH. 1/8 NPT 4 BLOCK | 5 | [26 empty] | 2026-04-29 | MACHINE (O) |  | MACHINE (O)
4465 | 60952 | FLO |  |  | 276269 | SPACER | 2 |  | HRPO | 1/2" | [23 empty] | 2026-04-29 | LASER CUT (O) |  | LASER CUT (O)
4440 | 60929 | FLO |  | 2026-04-29
4440 | 60929 | FLO |  |  | LM-220-1-.125 | MANIFOLD ELPH. 1/8 NPT SINGLE BLOCK | 10 | [26 empty] | 2026-04-29 | MACHINE (O) |  | MACHINE (O)
4440 | 60929 | FLO |  |  | 250286XMP | BRACKET, UV VALVE MOUNTING PAD BLOCK REV A | 200 | [14 empty] | 2026-04-28 | [11 empty] | 2026-04-29 | TAPPING |  | LASER CUT (O), TAPPING
4479 | 60981 | FLO |  | 2026-04-30
4479 | 60981 | FLO |  |  | LM-202 | ROCK FALL GUARD BLACK REV.A | 3 | [26 empty] | 2026-04-30 | WELD |  | WELD
4479 | 60981 | FLO |  |  | LM-202.1 | BODY | 2 |  | HRPO | 1/4" | [23 empty] | 2026-04-30 | CLEAN |  | LASER CUT, CLEAN, CSK, BEND
4479 | 60981 | FLO |  |  | LM-202.2 | BACK | 2 |  | HRPO | 1/4" | [23 empty] | 2026-04-30 | CLEAN |  | LASER CUT, CLEAN, CSK
4479 | 60981 | FLO |  |  | LM-202.3 | SIDE ANGLE | 4 |  | HRPO | 1/4" | [23 empty] | 2026-04-30 | CLEAN |  | LASER CUT, CLEAN, BEND
4462 | 95303 | ICON DIGITAL |  | 2026-04-30
4462 | 95303 | ICON DIGITAL |  |  |  | Small Quikstands Poles - 21 3/4” w x 55 1/8” h Base - 22 1/2” w x 13” | 15 | [23 empty] | 2026-04-27 |  |  | 2026-04-30 | WHOLE JOB |  | WHOLE JOB (O)
4453 | 95263 | ICON DIGITAL |  | 2026-04-30
4453 | 95263 | ICON DIGITAL |  |  |  | Medium Quick stand Stand -25.750" x 67.312" Base-26.375" x 13.5" | 100 | [23 empty] | 2026-04-27 |  |  | 2026-04-30 | WHOLE JOB |  | WHOLE JOB (O)
4490 | 261895 | ROSENBERG |  | 2026-05-01
4490 | 261895 | ROSENBERG |  |  | S11-28016 | MOTOR SUPPORT PLATE KHMER 280 Motor GD112, new 320 x 320 mm | 10 |  | G-90 | 14GA | 2026-04-23 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-30 | [15 empty] | 2026-05-01 | LASER CUT |  | LASER CUT, BEND
4490 | 261895 | ROSENBERG |  |  | S04-50043 | INLET CONE PLATE FOR ..KNOB/KB 500.B | 10 |  | G-90 | 11GA | 2026-04-23 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-30 | [15 empty] | 2026-05-01 | LASER CUT |  | LASER CUT, BEND
4490 | 261895 | ROSENBERG |  |  | S04-28002 | INLET CONE PLATE 280 430x430 / _KM 280 | 10 |  | G-90 | 14GA | 2026-04-23 | 2026-04-25 | 2026-04-25 |  |  |  |  | 2026-04-30 | [15 empty] | 2026-05-01 | LASER CUT |  | LASER CUT, BEND
4489 | 038631548-R0 | FLYNN | CAMH F - CW3 PW SHIM-003-01 & SHIM -004-01 - REORDER | 2026-05-01
4489 | 038631548-R0 | FLYNN |  |  |  | SHIM-003-01 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-04-29 | [17 empty] | 2026-05-01 | MATERIALS |  | MATERIALS, SAW
4489 | 038631548-R0 | FLYNN |  |  |  | SHIM-004-01 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-04-29 | [17 empty] | 2026-05-01 | MATERIALS |  | MATERIALS, SAW
4349 | 8100000674 | CITY OF TORONTO |  | 2026-05-01
4349 | 8100000674 | CITY OF TORONTO |  |  | Signage Base |  | 13 | [23 empty] | 2026-04-29 |  |  | 2026-05-01 | WHOLE JOB |  | ENGINEERING, TUBE LASER (O), WELD
4509 | 104061 | TAYCO |  | 2026-05-04
4509 | 104061 | TAYCO |  |  | 8485-081299_R00 8485-081299 | POWER BEAM TILE, METAL, 41"W, W/ PR & | 6 |  | CRS | 18GA | 2026-04-27 | 2026-04-29 | 2026-04-29 |  |  |  |  | 2026-05-01 | [15 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN, BEND
4507 | 104062 | TAYCO |  | 2026-05-04
4507 | 104062 | TAYCO |  |  | 8485-0917_R00 8485-0917 | Junction, Double Desk Base | 6 |  | HRPO | 11GA | [13 empty] | 2026-05-01 | [9 empty] | 2026-05-04 | WELD |  | WELD
4507 | 104062 | TAYCO |  |  | 8485-0917-BOTTOM R00 | BOTTOM FRAME | 6 | [5 empty] | 2026-04-27 |  |  |  |  | 2026-04-29 | [15 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN, BEND, WELD
4507 | 104062 | TAYCO |  |  | 8485-0917-TOP R00 | TOP FRAME | 6 | [5 empty] | 2026-04-27 |  |  |  |  | 2026-04-29 | [15 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN, BEND, WELD
4507 | 104062 | TAYCO |  |  | 8485-0917 CORNER BRKT R00 | CORNER BRACKET | 24 | [5 empty] | 2026-04-27 |  |  |  |  | 2026-04-29 | [15 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN, BEND, WELD
4507 | 104062 | TAYCO |  |  | 8485-0917 BRACE R00 | BRACE | 12 | [5 empty] | 2026-04-27 |  |  |  |  | 2026-04-29 | [15 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN, BEND, WELD
4507 | 104062 | TAYCO |  |  | 8485-2601341_R00 8485-2601341 | JUNCTION DOUBLE DESK COVER, 8.25" | 2 | [16 empty] | 2026-05-01 | [9 empty] | 2026-05-04 | WELD |  | WELD
4507 | 104062 | TAYCO |  |  | 8485-075691_frame | Junction, Double Desk Cover, Frame | 2 |  | HRS | 11GA |  |  | 2026-04-27 |  |  |  |  | 2026-04-29 | [15 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN, BEND
4507 | 104062 | TAYCO |  |  | 8485-2601341_tab | Junction, Double Desk Cover, Tab | 24 |  | HRS | 11GA |  |  | 2026-04-27 | [8 empty] | 2026-04-29 | [11 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN
4507 | 104062 | TAYCO |  |  | 8485-0848_R00 8485-0848 | Flip Flop Table - Modesty Bracket | 100 |  | HRS | 12GA |  |  | 2026-04-27 |  |  |  |  | 2026-05-01 | 2026-04-30 | [14 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN, BEND
4507 | 104062 | TAYCO |  |  | 8485-0449_R01 8485-0449 | COSMO, PANEL MOUNTED CANTILEVER, 10"D, RH | 4 | #VALUE! | HRPO | 12GA |  |  | 2026-04-27 |  |  |  |  | 2026-05-01 | 2026-04-30 | [14 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN, BEND
4507 | 104062 | TAYCO |  |  | 8485-0450_R01 8485-0450 | COSMO, PANEL MOUNTED CANTILEVER, 10"D, LH | 4 | #VALUE! | HRPO | 12GA |  |  | 2026-04-27 |  |  |  |  | 2026-05-01 | 2026-04-30 | [14 empty] | 2026-05-04 | LASER CUT |  | LASER CUT, CLEAN, BEND
4493 | MIS0071112 | G.W. ANGLIN |  | 2026-05-04
4493 | MIS0071112 | G.W. ANGLIN |  |  |  | T-GW-RODFORM-18 GWA RETAINER ROD-18 DRAWER | 300 | [23 empty] | 2026-05-01 |  |  | 2026-05-04 | WHOLE JOB |  | WHOLE JOB (O)
4492 | 40002438 | GINKGO |  | 2026-05-04
4492 | 40002438 | GINKGO |  |  |  | Splices 3" Height | 50 |  | ALUMINIUM | 16GA | 2026-04-22 |  | 2026-04-24 |  |  |  |  | 2026-05-01 | [11 empty] | 2026-04-27 |  |  |  | 2026-05-04 | LASER CUT |  | LASER CUT, BEND
4492 | 40002438 | GINKGO |  |  |  | 4" Height, 3"Flange, 1/2 X 1/2" Lip | 43 |  | ALUMINIUM | 16GA | 2026-04-22 |  | 2026-04-24 |  |  |  |  | 2026-05-01 | [11 empty] | 2026-04-27 |  |  |  | 2026-05-04 | LASER CUT |  | LASER CUT, PUNCH (O), BEND
4484 | 103955 | TAYCO |  | 2026-05-04
4484 | 103955 | TAYCO |  |  | 8393-0046 - REV 02 8393-0046 | TOP CONNECTOR 90 DEG | 200 |  | CRS | 12GA | 2026-04-20 |  | 2026-04-22 |  |  |  |  | 2026-05-01 | 2026-04-25 | 2026-04-29 |  | 2026-04-27 | [11 empty] | 2026-05-04 | CSK |  | LASER CUT, CLEAN, TAPPING, CSK, BEND
4483 | 103953 | TAYCO |  | 2026-05-04
4483 | 103953 | TAYCO |  |  | 8482-0009_R04 8482-0009 | SCREW & BRACKETS F/SLIDING DOORS/SCENE GLAZED DOOR | 500 |  | HRS | 12GA |  |  | 2026-04-20 |  |  |  |  | 2026-04-21 |  |  | 2026-04-22 | 2026-04-23 |  |  |  | 2026-04-26 | [7 empty] | 2026-04-27 | DRILL |  | LASER CUT, CLEAN, SPECIAL, TAPPING, PLATING (O)
4473 | 103886 | TAYCO |  | 2026-05-04
4473 | 103886 | TAYCO |  |  | 8485-0041-R01 8485-0041 | SEATED TABLE PLINTH GLIDE PLATE,1-7/8" X1-7/8",1/4 | 25 |  | HRPO | 1/4" | 2026-04-26 |  | 2026-04-28 | [5 empty] | 2026-04-30 |  |  | 2026-05-01 | [11 empty] | 2026-05-04 | TAPPING |  | LASER CUT, CLEAN, TAPPING
4455 | 103791 | TAYCO |  | 2026-05-04
4455 | 103791 | TAYCO |  |  | 8423-0056_R06 8423-0056 | CENTER STEEL TABLE LEGS 12" | 40 | [23 empty] | 2026-05-01 |  |  | 2026-05-04 | TUBE LASER (O) |  | TUBE LASER (O), WELD, CLEAN
4433 | 103720 | TAYCO |  | 2026-05-04
4433 | 103720 | TAYCO |  |  | 8485-0001-R05 8485-0001 | STEEL CABINET LEG MTG PLATE, 4" x 4", 1/4"TH | 400 |  | HRPO | 1/4" |  |  |  | 2026-05-01 | [19 empty] | 2026-05-04 | CLEAN |  | LASER CUT, CLEAN
4475 | 60971 | FLO |  | 2026-05-05
4475 | 60971 | FLO |  |  | LM-379 | GUARD CONTROL BOX HITACHI GREY | 1 |  | HRPO | 11GA | [23 empty] | 2026-05-05 | CLEAN |  | LASER CUT, CLEAN, BEND, WELD
4475 | 60971 | FLO |  |  | LM-399-2 | (E12682369) PUMP BRACKET | 2 |  | HRPO | 7GA | [23 empty] | 2026-05-05 | LASER CUT |  | LASER CUT, CLEAN, BEND
4475 | 60971 | FLO |  |  | LM-399-1 | (E12682295) PUMP COVER | 1 |  | HRPO | 7GA | [23 empty] | 2026-05-05 | LASER CUT |  | LASER CUT, CLEAN, BEND, WELD
4477 | 222 | KLIMATROL |  | 2026-05-07
4477 | 222 | KLIMATROL |  |  | KLIMACABI-48248 | Klimatrol White Surface Mount Cabinet 48X24X8.5 Dimension: 48"(Wide) X 24" High x 8" deep (Plus door) - depth is 8.5" with door | 3 |  |  |  | 2026-04-20 | 2026-04-23 | 2026-04-23 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-04-30 | 2026-04-28 |  |  |  | 2026-05-03 |  |  |  |  | 2026-05-05 | 2026-05-07 | LASER CUT |  | PAINT (O), ASSEMBLY
4477 | 222 | KLIMATROL |  |  | KLIMACABI-42248 | Klimatrol White Surface Mount Cabinet 42X24X8.5 Dimension: 42"(Wide) X 24" High x 8" deep (Plus door) - depth is 8.5" with door | 4 |  |  |  | 2026-04-20 | 2026-04-23 | 2026-04-23 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-04-30 | 2026-04-28 |  |  |  | 2026-05-03 |  |  |  |  | 2026-05-05 | 2026-05-07 | LASER CUT |  | PAINT (O), ASSEMBLY
4477 | 222 | KLIMATROL |  |  | KLIMACABI-343412 | Klimatrol White Surface Mount Cabinet 34X34X14.5 Dimension: 34"(Wide) X 34" High x 14" deep (Plus door) - depth is 14.5" with door | 3 |  |  |  | 2026-04-20 | 2026-04-23 | 2026-04-23 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-04-30 | 2026-04-28 |  |  |  | 2026-05-03 |  |  |  |  | 2026-05-05 | 2026-05-07 | LASER CUT |  | PAINT (O), ASSEMBLY
4477 | 222 | KLIMATROL |  |  | KLIMACABI-323212 | Klimatrol White Surface Mount Cabinet 32X32X12.5 Dimension: 32"(Wide) X 32" High x 12" deep (Plus door) - depth is 12.5" with door | 4 |  |  |  | 2026-04-20 | 2026-04-23 | 2026-04-23 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-04-30 | 2026-04-28 |  |  |  | 2026-05-03 |  |  |  |  | 2026-05-05 | 2026-05-07 | LASER CUT |  | PAINT (O), ASSEMBLY
4477 | 222 | KLIMATROL |  |  | KLIMACABI-48247 | Klimatrol White Surface Mount Cabinet 48X24X7 | 5 |  |  |  | 2026-04-20 | 2026-04-23 | 2026-04-23 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-04-30 | 2026-04-28 |  |  |  | 2026-05-03 |  |  |  |  | 2026-05-05 | 2026-05-07 | LASER CUT |  | PAINT (O), ASSEMBLY
4477 | 222 | KLIMATROL |  |  | KLIMACABI-42247 | Klimatrol White Surface Mount Cabinet 42X24X7 | 1 |  |  |  | 2026-04-20 | 2026-04-23 | 2026-04-23 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-04-30 | 2026-04-28 |  |  |  | 2026-05-03 |  |  |  |  | 2026-05-05 | 2026-05-07 | LASER CUT |  | 1
4477 | 222 | KLIMATROL |  |  | KLIMACABI-36247 | Klimatrol White Surface Mount Cabinet 36X24X7 | 13 |  |  |  | 2026-04-20 | 2026-04-23 | 2026-04-23 |  |  |  |  | 2026-04-25 |  |  |  |  | 2026-04-30 | 2026-04-28 |  |  |  | 2026-05-03 |  |  |  |  | 2026-05-05 | 2026-05-07 | LASER CUT |  | PAINT (O), ASSEMBLY
4511 | 104081 | TAYCO |  | 2026-05-11
4511 | 104081 | TAYCO |  |  | 8485-0658_R01 8485-0658 | Reception Proto [4], Base end cap, 1/8" AL, TYPE 2 | 8 |  | ALUMINIUM | 11GA | [23 empty] | 2026-05-11 | SHIP |  | LASER CUT, CLEAN
4510 | 104074 | TAYCO |  | 2026-05-11
4510 | 104074 | TAYCO |  |  | 8681-0032 R01 8681-0032 | LAM PED SUPPORT BRACKET.RH | 50 |  | HRPO | 12GA |  |  | 2026-05-03 |  |  |  |  | 2026-05-08 | 2026-05-05 | [14 empty] | 2026-05-11 | LASER CUT |  | LASER CUT, CLEAN, BEND
4508 | 104063 | TAYCO |  | 2026-05-11
4508 | 104063 | TAYCO |  |  | 8393-0070_R01 8393-0070 | SWITCH SHARED & SINGLE MOUNTING BRACKET 17" | 250 |  | HRS | 12GA |  |  | 2026-05-03 |  |  |  |  | 2026-05-08 | 2026-05-05 | [14 empty] | 2026-05-11 | LASER CUT |  | LASER CUT, BEND
4508 | 104063 | TAYCO |  |  | 8487-0022 R01 8487-0022 | WARM MT TLC VR, PR+DATA RH, FA/60W PL | 50 |  | CRS | 18GA |  |  | 2026-05-03 |  |  |  |  | 2026-05-08 | [15 empty] | 2026-05-11 | LASER CUT |  | LASER CUT, CLEAN, BEND
4508 | 104063 | TAYCO |  |  | 8487-0014 R01 8487-0014 | WARM MT TLC VR, PR+DATA AL, FA/60W PL | 50 |  | CRS | 18GA |  |  | 2026-05-03 |  |  |  |  | 2026-05-08 | [15 empty] | 2026-05-11 | LASER CUT |  | LASER CUT, CLEAN, BEND
4508 | 104063 | TAYCO |  |  | 8485-0765_R02 8485-0765 | GALLERY WALL FOOT U CHANNEL ELEMENT | 20 | [16 empty] | 2026-05-08 | [9 empty] | 2026-05-11 | WELD |  | WELD
4508 | 104063 | TAYCO |  |  | 8485-0052 | U CHANNEL, GALLERY WALL W SCREEN, 1.5" x 1-1/4" x 9", 1/8"TH | 20 |  | HRS | 11GA |  |  | 2026-05-02 |  |  |  |  | 2026-05-05 | [15 empty] | 2026-05-11 | LASER CUT |  | LASER CUT, CLEAN, BEND
4508 | 104063 | TAYCO |  |  | 8485-0053 | U CHANNEL MTG PLATE, GALLERY WALL W SCREEN, 1-1/8 x 1-5/16", 1/8"TH | 20 |  | HRS | 7GA |  |  | 2026-04-30 |  |  |  |  | 2026-05-05 | 2026-05-01 |  |  | 2026-05-02 | [11 empty] | 2026-05-11 | LASER CUT |  | LASER CUT, CLEAN, TAPPING, BEND
4500 | 104018 | TAYCO |  | 2026-05-11
4500 | 104018 | TAYCO |  |  | 8559118 | BRC ANTI-TIP BRACKET - PLATE | 250 |  | HRS | 10GA | 2026-04-25 |  | 2026-04-27 | [8 empty] | 2026-04-30 |  |  |  | 2026-05-08 | [7 empty] | 2026-05-11 | LASER CUT |  | LASER CUT, CLEAN, TAPPING, PLATING (O)
4494 | 44796 | HABCO |  | 2026-05-11
4494 | 44796 | HABCO |  |  | C068379 | BRACKET DR MTG TOP RETAINER TORSION SST | 560 |  | SS | 14GA | 2026-04-22 |  | 2026-04-22 | [5 empty] | 2026-04-23 |  |  | 2026-04-25 | [11 empty] | 2026-04-27 | CLEAN |  | LASER CUT, CLEAN, TAPPING
4494 | 44796 | HABCO |  |  | C068378 | BRACKET DR MTG TOP RETAINER TORSION SST | 560 |  | SS | 14GA | 2026-04-22 |  | 2026-04-22 |  |  |  |  | 2026-04-24 | 2026-04-23 | [12 empty] | 2026-04-25 |  | 2026-04-27 | CLEAN |  | LASER CUT, CLEAN, BEND, HARDWARE
4486 | 103959 | TAYCO |  | 2026-05-11
4486 | 103959 | TAYCO |  |  | 8393-0172_R00 8393-0172 | SWITCH FLIPPER CABINET SIDE - LH | 174 |  | CRS | 12GA | 2026-04-30 |  | 2026-05-05 |  |  |  |  | 2026-05-07 |  | 2026-05-09 | [13 empty] | 2026-05-11 | LASER CUT |  | LASER CUT, BEND, CLEAN
4486 | 103959 | TAYCO |  |  | 8393-0171_R00 8393-0171 | SWITCH FLIPPER CABINET SIDE - RH | 126 |  | CRS | 12GA | 2026-04-30 |  | 2026-05-05 |  |  |  |  | 2026-05-07 |  | 2026-05-09 | [13 empty] | 2026-05-11 | LASER CUT |  | LASER CUT, BEND, CLEAN
4485 | 103956 | TAYCO |  | 2026-05-11
4485 | 103956 | TAYCO |  |  | 8423-0058_R06 8423-0058 | ENTER STEEL TABLE LEGS 30" | 10 | [23 empty] | 2026-05-07 |  |  | 2026-05-11 | WHOLE JOB |  | WHOLE JOB (O)
4480 | CAP2604075 | KNC/KN |  | 2026-05-11
4480 | CAP2604075 | KNC/KN |  |  |  | SUPPLIER PART #:C-200D-134 GUIDE PLATE KNC PART #:C200D134GUIDEPLATE C-200D-134 GUIDE PLATE C/W COUNTER BORE STEEL ZINC PLATED | 1000 |  | HRPO | 11GA | 2026-04-25 |  | 2026-04-30 | [5 empty] | 2026-05-09 | 2026-05-07 | 2026-05-04 |  |  |  |  | 2026-05-11 | [7 empty] | 2026-05-11 | CSK |  | LASER CUT, CLEAN, CSK, PLATING (O)
4480 | CAP2604075 | KNC/KN |  |  |  | SUPPLIER PART #:C-200D-138 GUIDE PLATE KNC PART #:C200D138GUIDEPLATE C-200D-138 GUIDE PLATE C/W COUNTER BORE STEEL ZINC PLATED | 500 |  | HRPO | 11GA | 2026-04-25 |  | 2026-04-30 | [5 empty] | 2026-05-09 | 2026-05-07 | 2026-05-04 |  |  |  |  | 2026-05-11 | [7 empty] | 2026-05-11 | CSK |  | LASER CUT, CLEAN, CSK, PLATING (O)
4476 | 103911 | TAYCO |  | 2026-05-11
4476 | 103911 | TAYCO |  |  | 8393-0113_REV06 8393-0113 | SWITCH-PEDESTAL SP MOUNT BRACKET RH, FOR 24"D WS | 100 |  | CRS | 12GA | 2026-05-02 |  | 2026-05-05 |  |  |  |  | 2026-05-09 | 2026-05-08 | [14 empty] | 2026-05-11 | CLEAN |  | LASER CUT, CLEAN, BEND
4476 | 103911 | TAYCO |  |  | 8393-0112_REV06 8393-0112 | SWITCH-PEDESTAL SP MOUNT BRACKET AL, FOR 24"D WS | 100 |  | CRS | 12GA | 2026-05-02 |  | 2026-05-05 |  |  |  |  | 2026-05-09 | 2026-05-08 | [14 empty] | 2026-05-11 | CLEAN |  | LASER CUT, CLEAN, BEND
4498 | 7163 | GIVEX CANADA |  | 2026-05-12
4498 | 7163 | GIVEX CANADA |  |  |  | Angle Bracket for Bump Bar | 100 |  |  |  | 2026-04-28 |  |  |  |  | 2026-05-01 | [5 empty] | 2026-05-06 | [5 empty] | 2026-05-10 | [5 empty] | 2026-05-12 | MATERIALS |  | MATERIALS, SAW, TAPPING
4506 | 301830 | DAVIS STANDARD |  | 2026-05-13
4506 | 301830 | DAVIS STANDARD |  |  | CABC243012O 002218800-34-CAB1 + CABC243012O | CABINET, CS 24H X 30W X 12D, 1-DOOR, W/URBANELY, W/CUTOUTS FOR HANDLES AND 80MM SWINGER TOP/BOTTOM | 1 |  |  |  | 2026-04-27 | 2026-04-30 | 2026-04-30 |  |  |  |  | 2026-05-04 |  |  |  | 2026-05-04 | 2026-05-10 | 2026-05-08 | [9 empty] | 2026-05-13 | ENGINEERING |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4499 | 301704 | DAVIS STANDARD |  | 2026-05-13
4499 | 301704 | DAVIS STANDARD |  |  | CABC362412PB / - CABC362412PB + 002226456-3-CAB1 | CABC362412PB / - CABC362412PB + 002226456-3-CAB1 ENCLOSURE,N-12 WALL 36H X 24W X 12D INCLUDES URBANELY, PLUG PLATE BOTH SIDES | 1 |  |  |  | 2026-04-27 | 2026-04-30 | 2026-04-30 |  |  |  |  | 2026-05-04 |  |  |  | 2026-05-04 | 2026-05-10 | 2026-05-08 | [9 empty] | 2026-05-13 | LASER CUT |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4499 | 301704 | DAVIS STANDARD |  |  | CABC242410O / - CABC242410O + 002222827-47-CAB1 | CABC242410O / - CABC242410O + 002222827-47-CAB1 CABINET, CS 24H X 24W X 10D, 1-DOOR, W/URBANELY, W/CUTOUTS FOR HANDLES AND 80MM SWINGER TOP/BLOT | 1 |  |  |  | 2026-04-27 | 2026-04-30 | 2026-04-30 |  |  |  |  | 2026-05-04 |  |  |  | 2026-05-04 | 2026-05-10 | 2026-05-08 | [9 empty] | 2026-05-13 | LASER CUT |  | ENGINEERING, LASER CUT, TAPPING, BEND, WELD, GRIND
4512 | 44135 | THE WIRE MESH BELT | .192" dial 304 SS rods supplied | 2026-05-14
4512 | 44135 | THE WIRE MESH BELT |  |  |  | .192" dial 304 SS rods supplied | 1115 | [26 empty] | 2026-05-14
4487 | 103960 | TAYCO |  | 2026-05-18
4487 | 103960 | TAYCO |  |  | 8485-0001-R05 8485-0001 | STEEL CABINET LEG MTG PLATE, 4" x 4", 1/4"TH | 400 |  | CRS | 1/4" |  |  |  | 2026-05-15 | [19 empty] | 2026-05-18 | CLEAN |  | LASER CUT, CLEAN
4487 | 103960 | TAYCO |  |  | 8485-0000_R04 8485-0000 | SQ TUBE, 1" x 1", 16GA, 5-3/8"L, FOR CABINET LEG | 500 | [7 empty] | 2026-05-15 | [18 empty] | 2026-05-18 | TUBE LASER (O) |  | TUBE LASER (O)
4487 | 103960 | TAYCO |  |  | 8485-0007-R02 8485-0007 | SQ TUBE, 1" x 1", 16GA, 5-3/8"L,F/CRED SHAR | 100 | [7 empty] | 2026-05-15 | [18 empty] | 2026-05-18 | TUBE LASER (O) |  | TUBE LASER (O)
4502 | 44824 | HABCO |  | 2026-05-19
4502 | 44824 | HABCO |  |  | C068195 | BRACKET MOTOR DEC CONDENSER | 500 |  | G-90 | 16GA | 2026-05-02 |  | 2026-05-06 |  |  |  |  | 2026-05-11 | [15 empty] | 2026-05-12 | LASER CUT |  | LASER CUT, CLEAN, BEND
4460 | 261870 | ROSENBERG | AIR CHAMBER | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | BM Side Single Module | 4 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Door Side Single Module | 4 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Top Side Single Module | 4 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | OPP Side Single Module | 4 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | End Plate ingle odule | 4 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Door Weldment | 4 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Flange of Wall | 1 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Flange of Wall with Inner Flange | 1 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Settling Means Assembly (Perforated Panel + Mesh Panel) | 16 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Metric Nozzle | 1 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Door Hinge Plate | 16 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Vertical MTG Pad | 16 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Door Pin | 8 | [26 empty] | 2026-05-22
4460 | 261870 | ROSENBERG |  |  |  | Bushing | 22 | [26 empty] | 2026-05-22
4501 | 104019 | TAYCO |  | 2026-05-25
4501 | 104019 | TAYCO |  |  | 8390-0010-L R00 8390-0010-L | COSMO FLIPPER SIDE,COSMO FLIPPER LH SIDE, FORMEDSER CUT | 100 |  | CRS | 12GA |  |  | 2026-05-15 |  |  |  |  | 2026-05-20 | 2026-05-23 | [14 empty] | 2026-05-25 | LASER CUT |  | LASER CUT, BEND, CLEAN
4501 | 104019 | TAYCO |  |  | 8390-0010-R R00 8390-0010-R | COSMO FLIPPER COSMO FLIPPER RH SIDE, FORMED | 100 |  | CRS | 12GA |  |  | 2026-05-15 |  |  |  |  | 2026-05-20 | 2026-05-23 | [14 empty] | 2026-05-25 | LASER CUT |  | LASER CUT, BEND, CLEAN
4474 | 10388 | TAYCO |  | 2026-05-25
4474 | 10388 | TAYCO |  |  | 8485-0188 _R01 8485-0188 | LAPTOP TABLE RECTANGULAR TOP, 14" x 20", 1/4"TH | 44 |  | ALUMINIUM | 1/4" |  |  |  | 2026-05-17 |  |  |  |  | 2026-05-23 | [14 empty] | 2026-05-25 | LASER CUT (O) |  | LASER CUT (O)
4154 | P250288 | FURNACE BELT |  | 2026-06-01
4154 | P250288 | FURNACE BELT |  |  |  | SidePlate, Shingle, Tab Mount, 11GA, 310 STAINLESS Line Comment: STO875FB | 1896 |  | 310SS | 11GA | [7 empty] | 2026-05-27 | [15 empty] | 2026-06-01 | BEND |  | LASER CUT (O), BEND
4234 | P260013 | FURNACE BELT |  | 2026-08-03
4234 | P260013 | FURNACE BELT |  |  |  | SidePlate, Shingle, Tab Mount, 11GA, 310 STAINLESS STEEL SIA11-00C Line Comment: ST01OOFB | 2008 |  | 310SS | 11GA | [7 empty] | 2026-10-27 | [15 empty] | 2026-11-01 | BEND |  | LASER CUT (O), BEND
4234 | P260013 | FURNACE BELT |  |  |  | SidePlate, Shingle, Tab Mount, 11GA, 310 STAINLESS STEEL SIA11-00C Line Comment: ST01OOFB | 2008 |  | 310SS | 11GA | [7 empty] | 2026-10-27 | [15 empty] | 2026-11-01 | BEND |  | LASER CUT (O), BEND
4444 | 1081 | NEW EARTH |  | hold
4444 | 1081 | NEW EARTH |  |  | PLANTER MODIFICATION | 1. Cut down to 73 1/4" 2. Weld new cap 3. Metal rod in middle of planter, front to back, centred from the top and bottom (cant be visible when planted). 4. Paint to colour match | 1 |  | ALUMINIUM | 11GA | [23 empty] | hold | PAINT |  | LASER CUT, CLEAN, WELD, PAINT
4449 | 328 | TT PRECISION | CUTTING 2 HALVES OF ALUMINUM PROFILES 1/16" ALUMINUM THICKNESS
4449 | 328 | TT PRECISION |  |  |  | CUTTING 2 HALVES OF ALUMINUM PROFILES 1/16" ALUMINUM THICKNESS | 2
4448 | 327 | TT PRECISION | Squirt Event Pivot Stand (1-RHS/1-LHS "V") & Hing Clamp (1-"W")
4448 | 327 | TT PRECISION |  |  | SAMPLE T612-01A | Squirt Event Pivot Stand (1-RHS/1-LHS "V") & Hing Clamp (1-"W") | 1
4447 | 326 | TT PRECISION | 99-0871
4447 | 326 | TT PRECISION |  |  | 99-0871 |  | 20
4428 | 60908 | FLO
4428 | 60908 | FLO |  |  | LM-372 | BRACKET MOUNT SKF 203 PUMP REV C | 2026-10-20 |  | HRPO | 1/4" | [24 empty] | WELD |  | LASER CUT, CLEAN, BEND, WELD
4428 | 60908 | FLO |  |  | LM-230 | ROCK FALL GUARD (FENDER MOUNT) REV. J | 2 | [27 empty] | WELD |  | WELD
4120 | 1205 | ADVANCE PRODUCTS & SERVICES
4120 | 1205 | ADVANCE PRODUCTS & SERVICES |  |  | 89326MS | MANUFACTURE:Hinges:89326MS Large size hinge plate | 12 OUT OF 50PCS SHIPPED |  | HRPO | 3/8" | [24 empty] | SPECIAL |  | SPECIAL, BEND

## CALENDAR
CMF PRODUCTION CALENDAR — April 23, 2026
⚠ 1 OVERDUE process step(s) — shown in red at the top of each station column
MATERIALS (3) |  |  |  |  | ENGINEERING (24) |  |  |  |  | LASER CUTTING (52) |  |  |  |  | SAW / BANDSAW (3) |  |  |  |  | FORMING / BENDING (57) |  |  |  |  | CLEANING (19) |  |  |  |  | CSK / DRILL / TAPPING (26) ⚠1 |  |  |  |  | GRINDING (12) |  |  |  |  | WELDING (16) |  |  |  |  | OUTSIDE PROCESS (6) |  |  |  |  | PAINT / POWDER COAT (13) |  |  |  |  | SPECIAL / WHOLE JOB (10) |  |  |  |  | HARDWARE (2) |  |  |  |  | ASSEMBLY (11)
STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO | STATUS | DUE | COMPANY | WO # | PHOTO
▶ NOW | 4/25 | FLYNN | 4489 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | NEXT | 4/29 | FLYNN | 4489 |  | ▶ NOW | 4/23 | FLO | 4495 |  | ▶ NOW | 4/23 | HABCO | 4488 |  | ▶ NOW | 4/22 | TAYCO | 4483 |  | WAIT | 4/29 | DAVIS STANDARD | 4401 |  |  | 4/25 | HABCO | 4450 |  | WAIT | 4/26 | TAYCO | 4483 |  |  | 4/25 | KNC/KN | 4481 |  |  | 4/27 | HABCO | 4450 |  | WAIT | 4/25 | HABCO | 4488 |  | ▶ NOW | 4/24 | KLIMATROL | 4340
▶ NOW | 4/25 | FLYNN | 4489 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | NEXT | 4/29 | FLYNN | 4489 |  | ▶ NOW | 4/23 | FLO | 4495 |  | ▶ NOW | 4/23 | HABCO | 4488 |  |  | 4/23 | HABCO | 4450 |  | WAIT | 4/29 | DAVIS STANDARD | 4401 |  | WAIT | 4/28 | DAVIS STANDARD | 4401 |  | ▶ NOW | 4/27 | HABCO | 4450 |  | ▶ NOW | 4/25 | KNC/KN CROWDER | 4426 |  | ▶ NOW | 4/27 | HABCO | 4393 |  | WAIT | 4/25 | HABCO | 4494 |  | ▶ NOW | 4/24 | KLIMATROL | 4340
▶ NOW | 4/28 | GIVEX CANADA | 4498 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | NEXT | 5/1 | GIVEX CANADA | 4498 |  | ▶ NOW | 4/23 | TAYCO | 4467 |  | ▶ NOW | 4/23 | FLO | 4495 |  | ▶ NOW | 4/23 | TAYCO | 4467 |  | WAIT | 4/30 | KLIMATROL | 4477 |  | WAIT | 4/28 | DAVIS STANDARD | 4401 |  | ▶ NOW | 4/27 | HABCO | 4434 |  | ▶ NOW | 4/25 | KNC/KN CROWDER | 4426 |  | ▶ NOW | 4/27 | ICON DIGITAL | 4462 | [6 empty] | ▶ NOW | 4/24 | KLIMATROL | 4340
[5 empty] | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 | [6 empty] | NEXT | 4/24 | HABCO | 4488 |  | ▶ NOW | 4/23 | FLO | 4495 |  | NEXT | 4/23 | TAYCO | 4483 |  | WAIT | 4/30 | KLIMATROL | 4477 |  | WAIT | 4/28 | KLIMATROL | 4477 |  | WAIT | 5/8 | TAYCO | 4500 |  | ▶ NOW | 4/27 | W A ELECTRIC | 4412 |  | ▶ NOW | 4/27 | ICON DIGITAL | 4453 | [6 empty] | ▶ NOW | 4/24 | KLIMATROL | 4340
[5 empty] | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 | [6 empty] | NEXT | 4/24 | HABCO | 4494 |  | ▶ NOW | 4/23 | HABCO | 4494 |  | NEXT | 4/25 | HABCO | 4488 |  | WAIT | 4/30 | KLIMATROL | 4477 |  | WAIT | 4/28 | KLIMATROL | 4477 |  | WAIT | 5/11 | KNC/KN | 4480 |  | ▶ NOW | 4/27 | W A ELECTRIC | 4412 |  | NEXT | 4/27 | GINKGO | 4492 | [6 empty] | WAIT | 5/5 | KLIMATROL | 4477
[5 empty] | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 | [6 empty] | NEXT | 4/25 | TAYCO | 4482 |  | ▶ NOW | 4/23 | HABCO | 4494 |  | ▶ NOW | 4/25 | BVGLAZING SYSTEM | 4478 |  | WAIT | 4/30 | KLIMATROL | 4477 |  | WAIT | 4/28 | KLIMATROL | 4477 |  | WAIT | 5/11 | KNC/KN | 4480 |  | WAIT | 5/3 | KLIMATROL | 4477 |  | NEXT | 4/27 | GINKGO | 4492 | [6 empty] | WAIT | 5/5 | KLIMATROL | 4477
[5 empty] | ▶ NOW | 4/23 | KLIMATROL | 4477 |  | ▶ NOW | 4/23 | KLIMATROL | 4477 | [6 empty] | ▶ NOW | 4/25 | TAYCO | 4432 |  | NEXT | 4/30 | TAYCO | 4507 |  | ▶ NOW | 4/25 | TAYCO | 4459 |  | WAIT | 4/30 | KLIMATROL | 4477 |  | WAIT | 4/28 | KLIMATROL | 4477 | [6 empty] | WAIT | 5/3 | KLIMATROL | 4477 |  | ▶ NOW | 4/29 | CITY OF TORONTO | 4349 | [6 empty] | WAIT | 5/5 | KLIMATROL | 4477
[5 empty] | ▶ NOW | 4/24 | TAYCO | 4482 |  | ▶ NOW | 4/24 | TAYCO | 4482 | [6 empty] | NEXT | 4/25 | KLIMATROL | 4477 |  | NEXT | 4/30 | TAYCO | 4507 |  | ▶ NOW | 4/25 | BVGLAZING SYSTEM | 4446 |  | WAIT | 4/30 | KLIMATROL | 4477 |  | WAIT | 4/28 | KLIMATROL | 4477 | [6 empty] | WAIT | 5/3 | KLIMATROL | 4477 |  | ▶ NOW | 5/1 | G.W. ANGLIN | 4493 | [6 empty] | WAIT | 5/5 | KLIMATROL | 4477
[5 empty] | ▶ NOW | 4/24 | DAVIS STANDARD | 4401 |  | ▶ NOW | 4/24 | DAVIS STANDARD | 4401 | [6 empty] | NEXT | 4/25 | KLIMATROL | 4477 |  | NEXT | 4/30 | TAYCO | 4507 |  | ▶ NOW | 4/25 | BVGLAZING SYSTEM | 4446 |  | WAIT | 4/30 | KLIMATROL | 4477 |  | WAIT | 4/28 | KLIMATROL | 4477 | [6 empty] | WAIT | 5/3 | KLIMATROL | 4477 |  |  | 5/1 | TAYCO | 4455 | [6 empty] | WAIT | 5/5 | KLIMATROL | 4477
[5 empty] | ▶ NOW | 4/24 | DAVIS STANDARD | 4401 |  | ▶ NOW | 4/24 | DAVIS STANDARD | 4401 | [6 empty] | NEXT | 4/25 | KLIMATROL | 4477 |  | NEXT | 5/1 | TAYCO | 4508 |  | NEXT | 4/25 | HABCO | 4494 |  | WAIT | 5/10 | DAVIS STANDARD | 4506 |  | WAIT | 4/28 | KLIMATROL | 4477 | [6 empty] | WAIT | 5/3 | KLIMATROL | 4477 |  | ▶ NOW | 5/7 | TAYCO | 4485 | [6 empty] | WAIT | 5/5 | KLIMATROL | 4477
[5 empty] | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4505 |  | ▶ NOW | 4/24 | GINKGO | 4492 | [6 empty] | NEXT | 4/25 | KLIMATROL | 4477 |  | NEXT | 5/5 | TAYCO | 4510 |  | NEXT | 4/27 | DAVIS STANDARD | 4401 |  | WAIT | 5/10 | DAVIS STANDARD | 4499 |  | ▶ NOW | 5/1 | TAYCO | 4507 | [6 empty] | WAIT | 5/3 | KLIMATROL | 4477 | [11 empty] | WAIT | 5/5 | KLIMATROL | 4477
[5 empty] | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4504 |  | ▶ NOW | 4/24 | GINKGO | 4492 | [6 empty] | NEXT | 4/25 | KLIMATROL | 4477 |  | NEXT | 5/5 | TAYCO | 4508 |  | NEXT | 4/27 | DAVIS STANDARD | 4401 |  | WAIT | 5/10 | DAVIS STANDARD | 4499 |  | ▶ NOW | 5/1 | TAYCO | 4507 | [6 empty] | WAIT | 5/3 | KLIMATROL | 4477
[5 empty] | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4504 |  | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4505 | [6 empty] | NEXT | 4/25 | KLIMATROL | 4477 |  | ▶ NOW | 5/8 | TAYCO | 4476 |  | ▶ NOW | 4/28 | FLO | 4440 | [6 empty] | ▶ NOW | 5/8 | TAYCO | 4508 | [6 empty] | WAIT | 5/10 | GIVEX CANADA | 4498
[5 empty] | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4504 |  | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4504 | [6 empty] | NEXT | 4/25 | KLIMATROL | 4477 |  | ▶ NOW | 5/8 | TAYCO | 4476 |  | NEXT | 4/29 | TAYCO | 4507 | [6 empty] | WAIT | 5/8 | DAVIS STANDARD | 4506
[5 empty] | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4503 |  | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4504 | [6 empty] | NEXT | 4/27 | DAVIS STANDARD | 4401 |  | NEXT | 5/9 | KNC/KN | 4480 |  | ▶ NOW | 4/29 | TAYCO | 4484 | [6 empty] | WAIT | 5/8 | DAVIS STANDARD | 4499
[5 empty] | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4503 |  | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4504 | [6 empty] | NEXT | 4/27 | DAVIS STANDARD | 4401 |  | NEXT | 5/9 | KNC/KN | 4480 |  | NEXT | 4/30 | TAYCO | 4500 | [6 empty] | WAIT | 5/8 | DAVIS STANDARD | 4499
[5 empty] | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4503 |  | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4503 | [6 empty] | NEXT | 4/27 | ACTION HOME SERVICE | 4505 |  | WAIT | 5/23 | TAYCO | 4501 |  | ▶ NOW | 5/1 | TAYCO | 4473
[5 empty] | ▶ NOW | 4/25 | ROSENBERG | 4490 |  | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4503 | [6 empty] | NEXT | 4/27 | ACTION HOME SERVICE | 4504 |  | WAIT | 5/23 | TAYCO | 4501 |  | WAIT | 5/2 | TAYCO | 4508
[5 empty] | ▶ NOW | 4/25 | ROSENBERG | 4490 |  | ▶ NOW | 4/25 | ACTION HOME SERVICE | 4503 | [6 empty] | NEXT | 4/27 | ACTION HOME SERVICE | 4504 |  | NEXT | 5/23 | TAYCO | 4474 |  | NEXT | 5/4 | DAVIS STANDARD | 4506
[5 empty] | ▶ NOW | 4/25 | ROSENBERG | 4490 |  | ▶ NOW | 4/25 | ROSENBERG | 4490 | [6 empty] | NEXT | 4/27 | ACTION HOME SERVICE | 4504 | [6 empty] | NEXT | 5/4 | DAVIS STANDARD | 4499
[5 empty] | ▶ NOW | 4/29 | TAYCO | 4509 |  | ▶ NOW | 4/25 | ROSENBERG | 4490 | [6 empty] | NEXT | 4/27 | ACTION HOME SERVICE | 4503 | [6 empty] | NEXT | 5/4 | DAVIS STANDARD | 4499
[5 empty] | ▶ NOW | 4/30 | DAVIS STANDARD | 4506 |  | ▶ NOW | 4/25 | ROSENBERG | 4490 | [6 empty] | NEXT | 4/27 | ACTION HOME SERVICE | 4503 | [6 empty] | WAIT | 5/6 | GIVEX CANADA | 4498
[5 empty] | ▶ NOW | 4/30 | DAVIS STANDARD | 4499 |  | ▶ NOW | 4/27 | TAYCO | 4507 | [6 empty] | NEXT | 4/27 | ACTION HOME SERVICE | 4503 | [6 empty] | ▶ NOW | 5/7 | KNC/KN | 4480
[5 empty] | ▶ NOW | 4/30 | DAVIS STANDARD | 4499 |  | ▶ NOW | 4/27 | TAYCO | 4507 | [6 empty] | NEXT | 4/29 | TAYCO | 4507 | [6 empty] | ▶ NOW | 5/7 | KNC/KN | 4480
[10 empty] | ▶ NOW | 4/27 | TAYCO | 4507 | [6 empty] | NEXT | 4/29 | TAYCO | 4507 | [6 empty] | WAIT | 5/9 | TAYCO | 4486
[10 empty] | ▶ NOW | 4/27 | TAYCO | 4507 | [6 empty] | NEXT | 4/29 | TAYCO | 4507 | [6 empty] | WAIT | 5/9 | TAYCO | 4486
[10 empty] | ▶ NOW | 4/27 | TAYCO | 4507 | [6 empty] | NEXT | 4/29 | TAYCO | 4507
[10 empty] | ▶ NOW | 4/27 | TAYCO | 4507 | [6 empty] | NEXT | 4/29 | TAYCO | 4507
[10 empty] | ▶ NOW | 4/27 | TAYCO | 4507 | [6 empty] | NEXT | 4/30 | ROSENBERG | 4490
[10 empty] | ▶ NOW | 4/27 | TAYCO | 4507 | [6 empty] | NEXT | 4/30 | ROSENBERG | 4490
[10 empty] | ▶ NOW | 4/27 | TAYCO | 4507 | [6 empty] | NEXT | 4/30 | ROSENBERG | 4490
[10 empty] | ▶ NOW | 4/27 | TAYCO | 4500 | [6 empty] | NEXT | 5/1 | TAYCO | 4509
[10 empty] | ▶ NOW | 4/29 | TAYCO | 4509 | [6 empty] | WAIT | 5/1 | TAYCO | 4507
[10 empty] | ▶ NOW | 4/30 | TAYCO | 4508 | [6 empty] | WAIT | 5/1 | TAYCO | 4507
[10 empty] | ▶ NOW | 4/30 | DAVIS STANDARD | 4506 | [6 empty] | WAIT | 5/1 | TAYCO | 4507
[10 empty] | ▶ NOW | 4/30 | DAVIS STANDARD | 4499 | [6 empty] | WAIT | 5/1 | GINKGO | 4492
[10 empty] | ▶ NOW | 4/30 | DAVIS STANDARD | 4499 | [6 empty] | WAIT | 5/1 | GINKGO | 4492
[11 empty] | 5/1 | TAYCO | 4433 | [6 empty] | NEXT | 5/1 | TAYCO | 4484
[10 empty] | ▶ NOW | 5/2 | TAYCO | 4508 | [6 empty] | NEXT | 5/4 | DAVIS STANDARD | 4506
[10 empty] | ▶ NOW | 5/3 | TAYCO | 4510 | [6 empty] | NEXT | 5/4 | DAVIS STANDARD | 4499
[10 empty] | ▶ NOW | 5/3 | TAYCO | 4508 | [6 empty] | NEXT | 5/4 | DAVIS STANDARD | 4499
[10 empty] | ▶ NOW | 5/3 | TAYCO | 4508 | [6 empty] | NEXT | 5/5 | TAYCO | 4508
[10 empty] | ▶ NOW | 5/3 | TAYCO | 4508 | [6 empty] | WAIT | 5/5 | TAYCO | 4508
[10 empty] | ▶ NOW | 5/5 | TAYCO | 4486 | [6 empty] | NEXT | 5/7 | TAYCO | 4486
[10 empty] | ▶ NOW | 5/5 | TAYCO | 4486 | [6 empty] | NEXT | 5/7 | TAYCO | 4486
[10 empty] | ▶ NOW | 5/6 | HABCO | 4502 | [6 empty] | WAIT | 5/8 | TAYCO | 4510
[11 empty] | 5/15 | TAYCO | 4487 | [6 empty] | WAIT | 5/8 | TAYCO | 4508
[10 empty] | ▶ NOW | 5/15 | TAYCO | 4487 | [6 empty] | NEXT | 5/8 | TAYCO | 4508
[10 empty] | ▶ NOW | 5/15 | TAYCO | 4487 | [6 empty] | NEXT | 5/8 | TAYCO | 4508
[10 empty] | ▶ NOW | 5/15 | TAYCO | 4501 | [6 empty] | NEXT | 5/9 | TAYCO | 4476
[10 empty] | ▶ NOW | 5/15 | TAYCO | 4501 | [6 empty] | NEXT | 5/9 | TAYCO | 4476
[10 empty] | ▶ NOW | 5/17 | TAYCO | 4474 | [6 empty] | NEXT | 5/11 | HABCO | 4502
[20 empty] | NEXT | 5/20 | TAYCO | 4501
[20 empty] | NEXT | 5/20 | TAYCO | 4501
[20 empty] | ▶ NOW | 5/27 | FURNACE BELT | 4154
[20 empty] | ▶ NOW | 10/27 | FURNACE BELT | 4234
[20 empty] | ▶ NOW | 10/27 | FURNACE BELT | 4234

## TODAY
CMF PRODUCTION SCHEDULE — THURSDAY, APRIL 23, 2026 ¦ 1 OVERDUE • 26 DUE TODAY
ENGINEERING (7) | [5 empty] | LASER CUTTING (7) | [5 empty] | FORMING / BENDING (3) | [5 empty] | CLEANING (6) | [5 empty] | CSK / DRILL / TAPPING (4) ⚠ 1 OVERDUE
WO # | COMPANY | PART # | QTY | DUE | PHOTO | WO # | COMPANY | PART # | QTY | DUE | PHOTO | WO # | COMPANY | PART # | QTY | DUE | PHOTO | WO # | COMPANY | PART # | QTY | DUE | PHOTO | WO # | COMPANY | PART # | QTY | DUE | PHOTO
4477 | KLIMATROL | KLIMACABI-48248 | 3 | APR 23 |  | 4477 | KLIMATROL | KLIMACABI-48248 | 3 | APR 23 |  | 4495 | FLO | LM-556-R | 2 | APR 23 |  | 4488 | HABCO | C068379 | 600/750 | APR 23 |  | 4483 | TAYCO | 8482-0009_R04 8482-0009 | 500 | APR 22
4477 | KLIMATROL | KLIMACABI-42248 | 4 | APR 23 |  | 4477 | KLIMATROL | KLIMACABI-42248 | 4 | APR 23 |  | 4495 | FLO | LM-556-L | 2 | APR 23 |  | 4488 | HABCO | C068378 | 540/750 | APR 23 |  | 4450 | HABCO | C065980 | 40 | APR 23
4477 | KLIMATROL | KLIMACABI-343412 | 3 | APR 23 |  | 4477 | KLIMATROL | KLIMACABI-343412 | 3 | APR 23 |  | 4467 | TAYCO | 8390-0051_R01 8390-0051 | 50 | APR 23 |  | 4495 | FLO | LM-556-R | 2 | APR 23 |  | 4467 | TAYCO | 8390-0051_R01 8390-0051 | 50 | APR 23
4477 | KLIMATROL | KLIMACABI-323212 | 4 | APR 23 |  | 4477 | KLIMATROL | KLIMACABI-323212 | 4 | APR 23 | [7 empty] | 4495 | FLO | LM-556-L | 2 | APR 23 |  | 4483 | TAYCO | 8482-0009_R04 8482-0009 | 500 | APR 23
4477 | KLIMATROL | KLIMACABI-48247 | 5 | APR 23 |  | 4477 | KLIMATROL | KLIMACABI-48247 | 5 | APR 23 | [7 empty] | 4494 | HABCO | C068379 | 560 | APR 23
4477 | KLIMATROL | KLIMACABI-42247 | 1 | APR 23 |  | 4477 | KLIMATROL | KLIMACABI-42247 | 1 | APR 23 | [7 empty] | 4494 | HABCO | C068378 | 560 | APR 23
4477 | KLIMATROL | KLIMACABI-36247 | 13 | APR 23 |  | 4477 | KLIMATROL | KLIMACABI-36247 | 13 | APR 23